## Sheet1
Resources | Team | Task | Total Effort (weeks) | Total Cost (EGP) | Duration
CI/CD Tools | Development & DevOps Teams | Implement CI/CD pipelines | 2 | 6000 | 14/09/2024 - 28/09/2024
Cloud Infrastructure | DevOps Team | Set up auto-scaling for cloud resources | 3 | 6300 | 14/09/2024 - 04/10/2024
Backup & Recovery Automation | DevOps Team | Set up automated backups and recovery | 2 | 4200 | 01/10/2024 - 15/10/2024
Database Setup | 1 Database Admin | Set up database and configure storage | 4 | 14000 | 14/09/2024 - 15/10/2024
Security Features | 1 Security Specialist | Implement security features (HIPAA) | 4 | 16000 | 14/09/2024 - 01/11/2024
Content Licensing | Licensing Team | License healthcare content | 8 | 32000 | 14/09/2024 - 01/11/2024
Front-end Development | 2 Front-end Developers | Build and design front-end UI | 12 | 48000 | 14/09/2024 - 01/02/2025
Back-end Development | 2 Back-end Developers | Set up back-end systems and services | 14 | 56000 | 14/09/2024 - 15/02/2025
Branding | 1 Designer | Design brand identity | 2 | 7000 | 01/12/2024 - 15/12/2024
Hosting & Storage | 1 Cloud Engineer | Manage hosting and cloud storage | 8 | 20000 | 01/12/2024 - 01/02/2025
Content Acquisition | 1 Content Developer | Develop and acquire new content | 6 | 24000 | 01/10/2024 - 01/12/2024
Marketing & Promotion | Marketing Team | Promote the platform | 2 | 7000 | 01/04/2025 - 01/05/2025
Digital Advertising | 1 Marketing Specialist | Set up digital ads | 2 | 8000 | 01/04/2025 - 15/04/2025
Customer Support Setup | 1 Support Specialist | Set up customer support | 4 | 10000 | 01/03/2025 - 01/04/2025
Testing & QA | 2 QA Engineers | Conduct testing and quality assurance | 6 | 14000 | 01/03/2025 - 15/04/2025
Royalty Payments | Legal & Content Team | Handle royalty agreements and payments | 4 | 14000 | 15/01/2025 - 15/02/2025
Integration APIs | Development & Integration Teams | Integrate with other healthcare systems | 4 | 9800 | 16/11/2024 - 01/12/2024
Cloud Cost Management Tools | DevOps & Finance Teams | Optimize resource usage and costs | 2 | 3400 | 02/11/2024 - 15/11/2024
Monitoring Tools | Operations & DevOps Teams | Implement real-time monitoring & alerts | 3 | 6300 | 01/10/2024 - 21/10/2024
Security Compliance | Security & DevOps Teams | Encrypt data, set up compliance checks | 2 | 6000 | 22/10/2024 - 01/11/2024
Platform Development | Development Team | Develop the entire platform | 24 | 112000 | 14/09/2024 - 01/06/2025
AWS Infrastructure | Cloud Operations Team | Set up cloud infrastructure (AWS) | 16 | 56000 | 14/09/2024 - 01/06/2025
Operations & Miscellaneous | Operations Team | General operational costs | 12 | 20000 | 14/09/2024 - 01/06/2025
500000